## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2245-swen-261-02-2B-JellySolutions
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Cupboard page then I must see a means to navigate to the Needs page.
Given that I am not on the Cupboard page when I choose the Needs page then I am taken to the Needs page.
Given that I am on the Cupboard page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute.
Given that I am on the Cupboard page when there are needs in the cupboard then I see each need and short description.
Given that I am on the Cupboard page when there are needs in the cupboard then I see a means to add each need to my funding basket.
As a Developer I want to submit a request to input a username and a password so that each unique user can access their saved needs. | Given that I am on the u-fund site when I am not on the Login page then I must see a means to navigate to the Login page.
Given that I not on the Login page when I choose the Login page then I am taken to the Login page.
Given that I am on the Login page when I choose the Login page then I see a button to create an account.
Given that I am on the Login page when I choose the Login page then I see a prompt to input my username and password.
Given that I am on the Login page when I enter the correct username and password for a registered account then I am redirected to the home page.
Given that I am on the Login page when I enter an incorrect username or password for a registered account then I see a message that either the username or password I entered is incorrect.
Given that I am on the Login page when I choose the Login page then I see a button for forgot password.
Given that I am on the Forgot Password page when I choose the Forgot Password button then I see a prompt to input my email.
Given that I am on the Forgot Password page when I submit my email then I am redirected to a password recovery page to submit the verification code sent to my email.
Given that I am on the Password Recovery page when I submit the correct verification code then I see a prompt to submit my new password and re-enter it for confirmation.
As a helper I want to see a home page (u-fund site) so that I can navigate the website. | Given that I am on the u-fund site when there are needs in the cupboard then I see a preview of the needs in the cupboard.
Given that I am on the u-fund site when I am logged in and there are no needs in the cupboard then I see a message indicating that there are no needs available to contribute.
Given that I am on the u-fund site when I am logged in and there are needs in the cupboard then I must see a view more button to view the full cupboard.
Given that I am on the u-fund site when I click the searchbar then I must be able to submit a search term to search for needs.
Given that I am on the u-fund site when I am logged in and click the funding basket then I am redirected to the funding basket page.
Given that I am on the u-fund site when I click the Login page then I am redirected to the Login page.
Given that I am on the u-fund site when I am logged in then I must see a button to view my account information.
Given that I am on the u-fund site when I am logged in then I must see a button to log out.
As a helper I want to see a need page so that I can view the details of the need. | Given that I am on the Cupboard site when I am not on the Need page then I must see a means to navigate to the Need page.
Given that I am on the Need page when I am on the Need page then I see the need type.
Given that I am on the Need page when I am on the Need page then I see a summary about the need .
Given that I am on the Need page when I am on the Need page then I see a means to add the need to my funding basket.
Given I have logged into the website when I access the homepage then I expect CSS styles to be presented when the HTML is served.
As a developer I want to implement basic, functional CSS for components and pages so that there is basic formatting that can be navigated. | Given the backend and frontend are connected when I press a button on the website then I expect the backend to be updated.
As a Developer I want to connect our Rest backend with our Angular frontend so that they can interact with each other.