## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2245-swen-261-02-2B-JellySolutions
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Cupboard page then I must see a means to navigate to the Needs page. | ✔ | AK, 3/17/25
| Given that I am not on the Cupboard page when I choose the Needs page then I am taken to the Needs page. | ✔ | AK, 3/17/25
| Given that I am on the Cupboard page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | ✔ | AK, 3/17/25
| Given that I am on the Cupboard page when there are needs in the cupboard then I see each need. | ✔ | AK, 3/17/25
| Given that I am on the Cupboard page when there are needs in the cupboard then I see a means to add each need to my funding basket. | ✔ | HH, 3/29/25
As a Developer I want to submit a request to input a username and a password so that each unique user can access their saved needs. | Given that I am on the u-fund site when I am not on the Login page then I must see a means to navigate to the Login page. | ✔ | AK, 3/17/25
| Given that I not on the Login page when I choose the Login page then I am taken to the Login page. | ✔ | AK, 3/17/25
| Given that I am on the Login page when I choose the Login page then I see a button to create an account. | ✔ | AK, 3/17/25
| Given that I am on the Login page when I choose the Login page then I see a prompt to input my username and password. | ✔ | AK, 3/17/25
| Given that I am on the Login page when I enter the correct username and password for a registered account then I am redirected to the home page. | ✔ | AK, 3/17/25
| Given that I am on the Login page when I enter an incorrect username or password for a registered account then I see a message that either the username or password I entered is incorrect. | ✔ | AK, 3/17/25. Passes, as for the demo, all accounts are created if they don't exist.
As a helper I want to see a home page (u-fund site) so that I can navigate the website. | Given that I am on the u-fund site when there are needs in the cupboard then I see a preview of the needs in the cupboard. | ✔ | AK, 3/17/25
| Given that I am on the u-fund site when I am logged in and there are needs in the cupboard then I must see a view more button to view the full cupboard. | ✔ | AK, 3/17/25. All needs are viewable at all times on the cupboard.
| Given that I am on the u-fund site when I click the searchbar then I must be able to submit a search term to search for needs. | ✔ | AK, 3/17/25
| Given that I am on the u-fund site when I am logged in and click the funding basket then I am redirected to the funding basket page. | ✔ | AK, 3/17/25
| Given that I am on the u-fund site when I click the Login page then I am redirected to the Login page. | ✔ | AK, 3/17/25
| Given that I am on the u-fund site when I am logged in then I must see a button to view my account information. | ✔ | AK, 3/17/25. Passes. Can see username at top of page.
| Given that I am on the u-fund site when I am logged in then I must see a button to log out. | ✔ | AK, 3/17/25
As a helper I want to see a need page so that I can view the details of the need. | Given that I am on the Cupboard site when I am not on the Need page then I must see a means to navigate to the Need page. | ✔ | AK, 3/17/25
| Given that I am on the Need page when I am on the Need page then I see the need type. | ✔ | AK, 3/17/25
| Given that I am on the Need page when I am on the Need page then I see a summary about the need . | ✔ | AK, 3/17/25
| Given that I am on the Need page when I am on the Need page then I see a means to add the need to my funding basket. | ✔ | AK, 3/17/25
As a developer I want to implement basic, functional CSS for components and pages so that there is basic formatting that can be navigated. | Given I have logged into the website when I access the homepage then I expect CSS styles to be presented when the HTML is served. | ✔ | AK, 3/17/25
As a Developer I want to connect our Rest backend with our Angular frontend so that they can interact with each other. | Given the backend and frontend are connected when I press a button on the website then I expect the backend to be updated. | ✔ | AK, 3/17/25
AS a Developer I want api keys to be removed when expired SO THAT hundreds of expired keys do not pile up. | Given I am signed in when enough time passes then I expect my session to automatically end and be kicked back to the sign in page. | ✔ | HH, 3/29/25
| Given My session expires when my API key is too old then I expect it to be automagically removed from the database's user obje | ✔ | HH, 3/29/25
As a user I want to put in my password so that my account is secure. | GIVEN I submit a request to sign in WHEN the correct password is supplied THEN the system should log me in and return a status code of 200 (OK). | ✔ | HH, 3/29/25
| GIVEN I submit a request to sign in WHEN the incorrect password is supplied THEN the system should not log me in and return a status code of 401 (UNAUTHORIZED). | ✔ | HH, 3/29/25
AS a user I WANT to see a simple signup page SO THAT I can easily create an account without confusion. | Given I am on the login page when I click signup then I expect to be taken to the login page | ✔ | HH, 3/29/25
| Given I am entering a password when I input an invalid password (e.g., too short, missing special characters), then an error message must be displayed explaining the password requirements. | ✔ | HH, 3/29/25
| Given I have entered a password, when I confirm my password, then both passwords must match, or an error message should appear. | ✔ | HH, 3/29/25
| Given I have completed all required fields correctly when I attempt to submit the form then the signup button should be enabled. | ✔ | HH, 3/29/25
AS a Developer I WANT to submit a request to edit an existing need through the existing need-list-component, SO THAT it is added to the cupboard in a consistent way.. | Given I am an admin when I open the update form then I want to see a need-list that allows me to select a given need. | ✔ | HH, 3/29/25
| Given I am an admin when I submit the update form then I want the need's id to be automatically submitted based on my selection | ✔ | HH, 3/29/25
AS a Developer I WANT the same code to be reused SO THAT the display for search is uniform. | Given I search inside the need-list-component when valid results are returned then I want the display to utilize the existing need-list. | ✔ | HH, 3/29/25
| Given I do not search or have too broad results when the need list is being used then I want the current functionality to remain the same. | ✔ | HH, 3/29/25
As a user I want needs to be sorted so that information based on current needs can be accessed more efficiently and consistently across all need-list-components based on drop-down options. | GIVEN I click an option on the dropdown for sort WHEN viewing need search results and default display THEN I expect the results to be sorted by the selected criteria. | ✔ | HH, 3/29/25
AS a user I WANT to see a clear and navigable login page SO THAT I can easily login or create a new account. | Given I access any component or page when I am editing or viewing information in the app then I expect the user experience to be uniform and as clear as possible. | ✔ | HH, 3/29/25
As a user I want to be able to quickly view and understand needs without opening their dedicated component page. | GIVEN I am in the cupboard WHEN viewing needs THEN I expect to see some details of a need. | ✔ | HH, 3/29/25
AS a User I WANT my login to be saved for a while SO THAT I do not have to login multiple times. | Given I login to the service when I refresh the page then I expect to still be logged in. | ✔ | HH, 3/29/25
| Given I have been idle on a page for a long time when I refresh the page or perform an API interaction then I expect to get logged out. | ✔ | HH, 3/29/25